## Progress by Date
Date | Working Progress | Remark
2022-01-19 | Preparing Development Enviroment
2022-01-20 | Installation and Testing Postgres Database
2022-01-24 | Installation and Training Rabbit MQ
2022-01-25 | Initializing and Training dotnet and Web API
2022-01-26 | Training DI- Dependency Injection
2022-01-27 | Web API - with DI integrating creaing Aplus seed project
2022-01-31 | Defining and designing coding writing style
2022-02-01 | Testing and Defining communication with WEB API with postgresql
2022-02-02 | Testing and Integrating with Mass Transit Library for Queuing
2022-02-03 | Creating Data Service - base service to connect db and other service layer, Initialization of Flutter for mobile development
2022-02-08 | Creating Token Service - for Generating and Validation token
2022-02-09 | Modified Data Service
2022-02-10 | Creating OTP Service for one time password
2022-02-15 | Creating Credential Service - for login and Registeration
2022-02-16 | Making Database and API Design for Credential Service
2022-02-17 | Creating File Service for upload download File
2022-02-21 | Training and Testing Docker Contianer
2022-02-22 | Training and Testing Kong API Gateway
2022-02-23 | Creating Email Service - for sending application email
2022-03-01 | Desingning and Analyzing KYC Service
2022-03-03 | Creating KYC Service
2022-03-07 | Analyzing Aplus login flow and discussion with Khant Bone

## Working and Done Processes
Current Workdone
Enviroment
Postgrest SQL installation & configuration Done
Rabbit MQ Installation & configuration Done
Kong API Gateway Installation & configuration Done
Docker installation & configuration Done
Mobile Development
Flutter Framework setup
UI/UX and making components
Login
Registeration - Progress
API integration - Progress
Backend Development
Data Service
Token Service
Authentication Service
OTP Service
Credential Service
Email Service
File Service
KYC Service - Progress
Notification Service - Progress
Training
Docker training
Web API and DI Training
Rabbit MQ Training
Kong Training - Progress